Date: March 14, 2026
 Event: CRCNA Convention (Nov 13–15, 2026, Denver Marriott Tech Center)

## 1. Opening

- Roll call conducted

- Service Prayer and 12 Concepts read

- Agenda reviewed and approved

## 2. Treasurer’s Report (JR)

Treasurer - CRCNA_XL_Budget_2026_Final_Report.pdf

- Beginning balance: $9,823.32

- Outstanding: $450 (church sponsor breakfast)

- Debit card issues being resolved

- Financial records and budgets are up to date

## 3. Subcommittee Reports

### Hospitals & Institutions (H&I)

H & I - CRCNA XL    3-14-26      H&I Report.docx

- Budget: $1,250

- Plans:

  - Newcomer packets

  - H&I training session

  - Potential prison outreach during convention

### Program Committee (Dave)

Program Committee Report 2026-03-14.pdf

Programs - CRCNA XL Program Budget.pdf

Programs - Sponsor_Sponsee Breakfast Meeting Format.pdf

- Budget: $2,450

- Focus:

  - Increased travel costs for speakers

  - Seeking more in-state speakers

  - Speaker submission deadline: April 30, 2026

  - Sponsor-sponsee breakfast planning underway

### Merchandise (Dennis)

Merch - CRCNA XL  3-14-26 Merchandise Report.docx

- Budget:

  - Convention: $15,455

  - Pre-convention: $3,145.25

- Vendor:

  - Canadian supplier selected Tax and Tariff Implications When Using a Canadian Vendor in the USA Selling Their Products.pdf

  - Contract pending CNAC review

  - Verifying U.S. business status (tariff/legal considerations)

- Sales schedule:

  - Jewelry: Friday morning

  - General merchandise: Saturday at 3 PM

- Next meeting: April 20, 2026 (5:30 PM)

### Registration (Kathleen)

Registration - 3 CRCNA XL Registration Report.pdf

Registration - CRCNA XL March Agenda Registration .pdf

Registration - CRCNA XL Reg Budget.xlsx

Registration - sales-summary-2026-03-14-2026.pdf

- Early bird full package: $170

- Considering changes to registration packets

- Logistics planning in progress

### Web / Communications (Dan)

- Website improvements ongoing

- Mobile display issue under investigation

- Monthly CRCNA broadcast email to be launched

- Payment integrations discussed (PayPal, WooCommerce, Square)

## 4. Logo & Branding

Print and Display - CRCNA XL PD Budget.xlsx

- Final vote results:

  - Option 1 selected as primary logo (majority vote)

  - Option 9 selected for promotional use

- Adjustments to be made:

  - Ensure correct NA symbolism (12 steps)

  - Add CRCNA text and color variations

- Final version due by Monday for banner production

## 5. Event Planning

Entertainment - CRCNA Entertainment Budget.xlsx

### Sponsor–Sponsee Breakfast (March 21, 2026)

- Logistics discussed:

  - Table arrangements and floor plan

  - Smoking area setup (cones, cans, ashtrays)

  - Equipment (podium/mic pending venue confirmation)

  - Supplies (raffle tickets, trash bags, tablecloths)

- Cleanup responsibilities and venue coordination in progress

## 6. Additional Business

- Broadcast Communication

  - Monthly email updates to fellowship

  - Area liaisons to submit email contacts

- Social Media

  - Ad hoc committee to create guidelines (admin rotation, reporting)

- Merchandise Operations

  - Training on Square payment system

  - Emphasis on secure handling of funds

- Upcoming Events

  - Unity Day & Chili Cook-Off (April 11)

  - Men’s Retreat

  - Women’s Retreat

- Committee Needs

  - Open roles: Entertainment, Hotel & Hospitality, Print & Display

  - Volunteer recruitment to be announced at breakfast event

- Equipment

  - Missing PA system to be located and retrieved

## 7. Action Items (Key Highlights)

- Finalize logo and order banner

- Submit and review merchandise vendor contract

- Resolve website mobile issue

- Prepare and send monthly broadcast email

- Confirm breakfast logistics and supplies

- Recruit volunteers for open committee positions

## 8. Adjournment

- Meeting concluded with ongoing coordination for upcoming events and deliverables